FY2008 Work Plan For

NOAA’s Climate Observations Program

High Resolution Climate Data From Research and Volunteer Observing Ships

November 2007

Period covered by this workplan: Oct 1, 2007 - Sept 30, 2008

Project Manager: C. W. Fairall, Chief of Weather and Climate Physics Branch

Physical Science Division

NOAA Earth System Research Laboratory, 325 Broadway, Boulder, CO 80305

303-497-3253 Chris.Fairall@noaa.gov

Finance Contact: Jo Novosel, 303-497-6588 Jo.Novosel@noaa.gov

Lab Director: William D. Neff

PROJECT SUMMARY

This project involves the measurement of direct high-resolution air-sea fluxes on one to two cruises per year and the development of a roving standard flux measuring system to be deployed on a series of NOAA and UNOLS research vessels to promote the improvement of climate-quality data from those platforms.  An adjunct task is maintenance and operation of the C-band scanning Doppler radar and the stabilized wind profiling radar on the NOAA ship Ronald H. Brown.  Because buoys and most ships and satellites rely on bulk methods to estimate fluxes, another aspect of this project is the use of direct measurements to improve the NOAA/COARE bulk flux algorithm.  Originally one cruise was the annual TAO buoy tending cruise to 95 and 110 W on the Ronald Brown, but that has been discontinued in favor of an annual cruise to the equatorial Atlantic Ocean with Dr. Bob Molinari (AOML) as part of the African Multidisciplinary Monsoon Analyses (AMMA) and Saharan Dust studies.  The second cruise, which also occurs in the fall, is the annual excursion to turn around the Stratus climate buoy at 20 S 85 W.  A full suite of direct, inertial-dissipation, and bulk turbulent fluxes are measured along with IR and solar radiative fluxes, precipitation, and associated bulk meteorological properties.  This effort represents a partial transition of research from the OGP CLIVAR PACS program to operations under the Climate Observations Program (COP).

The project development is the result of a recent NOAA-sponsored workshop on high-resolution marine measurements (Smith et al., 2003, Report and Recommendations from the Workshop on High-Resolution Marine Meteorology, COAPS Report 03-01, Florida State University, pp38) which identified three important issues with the planned NOAA air-sea observation system: 1) the need for a data quality assurance program to firmly establish that the observations meet the accuracy requirements, 2) the need for observations at high time resolution (about 1 minute), 3) and the need to more efficiently utilize research vessels, including realizing their potential for the highest quality data and their potential to provide more direct and comprehensive observations.  For seasonal time scales, the net air-sea flux (sum of 5 flux components) must be constrained within 10 Wm-2.  Buoys and VOS systems are required to operate virtually unattended for months, so considerations of practical issues (e.g., power availability, instrument ruggedness, or safe access) are balanced against inherent sensor accuracy and optimal sensor placement.  As discussed above, an important function of the in situ measurements is to provide validation data to improve NWP and satellite flux fields.  Here, high time resolution and more direct observations are invaluable for interpreting surface flux measurements and diagnosing the source of disagreements; such information can be provided by suitably equipped research vessels (R/V). Thus, the accuracy of buoy and VOS observations must be improved and supplemented with high-quality, high time resolution measurements from the US R/V fleet (which is presently underutilized).  The necessity for both high time resolution and high accuracy places extreme demands on measurements because some sources of error (such as the effect of ship flow distortion on wind speed) tend to average out over a large sample.  To accomplish this task will require a careful intercomparison program to provide traceability of buoy, VOS, and RV accuracy to a set of standards.

This project directly addresses the need for accurate measures of air-sea exchange (Sections 5.2 to 5.4, Program Plan for Building a Sustained Ocean Observing System for Climate.  The project is a joint effort by ESRL and Dr. Robert Weller of the Woods Hole Oceanographic Institution (WHOI).  NOAA COP funds the ESRL component and Dr. Weller is seeking NSF fund for the WHOI component. The ESRL Air-Sea Interaction Group website can be found at: http://www.etl.noaa.gov/et6/air-sea/.  ESRL also cooperates with Dr. Andy Jessup (APL University of Washington) on radiative sea surface temperature measurements, Dr. Frank Bradley (CSIRO, Canberra Australia) on precipitation, Drs. M. Cronin and N. Bond (PMEL) on buoy-ship intercomparisons and climate variability analysis, and Dr. Mike Reynolds (DOE BNL) on radiative fluxes.  A new website is under construction for this project (High Resolution Climate Observations http://www.esrl.noaa.gov/psd/psd3/air-sea/oceanobs/ ).  An associated website (http://www.esrl.noaa.gov/psd/psd3/wgsf/ ) contains a handbook on best practices for flux measurements plus a database of high-resolution flux data.  This work will be closely monitored by the new WCRP Working Group on Surface Fluxes (WGSF) which is chaired by C. Fairall.  This will give the project high visibility in the CLIVAR, GEWEX, and SOLAS programs.  This project will be managed in cooperation with JCOMM (and other) panels as per instructions of Mike Johnson.

FY2008 PLANS

The major effort in FY07 will be execution of the two climate cruises (PNE 0AMMA/Saharan Dust-III and WHOI climate buoy cruises), and continued work on the Ronald Brown C-band radar.  Approximately 30 days of air-sea flux data will be obtained on the AMMA-III cruise and about 20 days of data on the WHOI cruise (Stratus2007).  The AMMA cruise is being done as a transition of the project from 6 years of East Pacific TAO cruises to begin gather data in the Atlantic.  The Stratus2007 cruise will be our fifth cruise to 25 S 85 W at the WHOI flux reference site.

A second component will be the inaugural deployment of the roving flux standard.   Our plan is to install the system in March 2008 on the WHOI R/V Knorr as part of the NOAA  ICEALOT study (http://saga.pmel.noaa.gov/Field/icealot/ ) in the Arctic, which is part of the International Polar Year research.  The standard will be loaded March 17 in Boston and end April 28 in Iceland (with a port stop in Tromso, Norway).

We have been advising the US Coast Guard on meteorological instrumentation for the Icebreaker R/V Healy.  They are installing a completely new instrument suite.  Dan Wolfe will make a trip to Seattle in November for initial discussions.  A second trip is planned for their shakedown cruises in January – February.

Construction will continue on the High Resolution Climate Observations website.  Since the flux handbook has been completed, the main task will be creating an online version (in cooperation with Shawn Smith at FSU). We also plan to update our ship data base so that all cruises through 2005 are publicly available.  Joint analysis projects with WHOI and PMEL will continue.

For the Ronald Brown radar systems project, a major maintenance is planned this year for the C-Band radar; most of the funds for this will come from other sources.  The Viasala (formerly SIGMET) IRIS software licenses and maintenance will also need to be continued (this is k$9 per year).  In the near future we may need to install a completely new version of the software at significant expense.  We are pursuing separate funds to do this.

We will continue our cooperation with Huai-Min Zhang of NOAA NCDC on the SURFA project.  The SURFA project is in an exploratory/setup phase.  We have started archiving surface flux fields from the ECMWF and NCEP operational global forecast models.  During the next year we will expand the archiving of surface data sets and do some preliminary evaluations of the data.

Outreach efforts during the reporting period center on educational contacts through the University of Colorado CIRES Outreach program and the NOAA Teacher-at-Sea program.  For the TAO cruise a link has been set up for twice-weekly exchanges with 10 middle school classes around the US.  This project has been dubbed ‘Ocean Interactions’ and can be found at: http://cires.colorado.edu/~k12/interactions/.  The fall 2007 WHOI climate buoy cruise will have one NOAA Teacher-at-Sea on board.

FY2008 BUDGET SUMMARY

The total ESRL request to OCO for this project is k$356 in FY2007.  This is augmented by k$25 in PI salary and about 50 k$ in other ESRL base contributions (salary, travel, etc).  The OCO budget breakdown is as follows

Salaries, including overhead			145

Capital equipment				  80

Travel						  32

Shipping					  20

Supplies					    7

Sondes					  	  18

Misc						    6

IT support					  24

Admin support				  28

The breakdown of this budget is as follows: operations - 70%, data management - 10%, R&D - 20%.  The program supports 0.83 federal FTE and 0.37 non Federal FTE; 0.30 Fed FTE are devoted to the project but not funded by it.  See attached budget page for details.

DELIVERABLES

*Stratus2007 cruise – Obtain flux data, fall cruise to WHOI climate reference buoy at 25 S 85W.  NOAA Ship Ronald H. Brown.

*Flux standard deployment R/V Knorr, March 17 – April 28, 2008.

*AMMA/African Dust cruise – Obtain flux data, April - May cruise to Eastern Atlantic, NOAA Ship Ronald H. Brown.

*Process and post Stratus2006 and AMMA data to ESRL/PSD data archive.

*Visit R/V Healy to advise on climate quality measurements.

*Write a report on evaluation of climate quality meteorological observations on R/V Ronald H. Brown based on entire PSD database on that ship.

*Submit (jointly with WHOI) paper on intercomparison of ship-based and buoy fluxes at WHOI stratus buoy site.