## Sheet1
About this File - Daily log files were not created daily during the last part of Leg II from Feb 17 to Mar 1 at which time Cox/Hutchinson began generating daily logs. This is a summary of notes that were taken by T. Uttal about events that would have been recorded in the daily_logs from Feb 17 through Mar 4.
2/17/2020 - On Feb 16 a large crack ran through the runway across the bow and then took a sharp, almost 90 degree turn to the south away from Met City. On Feb 17 a little hairline crack was observed to run from the turn straight through Met City and between the Met City Hut and the 11 meter tower. This crack never opened or developed. Matlab code to generate tower browse products was still not working - this was because of the power outage on the 15th. Because the matlab code checks backwards for 2 days, it was failing on what must have been missing or irregularly sized files. L1 had a 132 kb slow files, L2 had 446,629 kb fast, 1604 met and 1115 slow. All tower files were normal sizes
2/18/2020 - Egon and Anya were out at met city to check their eddy correlation system and as requested by T. Uttal confirmed that there was no movement or development of the hairline crack. On this day it was possible to run the matlab code to generate tower browse products for Feb 17. All looked good. L1 had a file size of 63 kb slow. fast and met are turned off. L2 had files sizes of 551671 kb fast (accumulating again), 1390 kb met and 1112 kb slow. All tower files were normal sizes. L2 continues to have excellent data recovery over radio. L1 barely reporting.
2/19/2020 - Windy and blowing snow. Several non-threatening cracks in the area around met city, 1 m (not so close) to 1 cm (through met city), but nothing moving. Cracks are filled with snow and difficult to see. Snow depth under VISSS is 60 cm and the bottom of the slave camera box is about 90 cm. The FMI rack is about 1 m above the surface. Both of these installations are noticably closer to the surface. The hut is in an increasingly large hole. LIghts were plugged in to be able to observe cracks activity from the bridge. Checked the rocket traps. These were turned already into the wind. THere is a crack immediately adjacent to the rocket crack that just missed seperating the mast from one of the guide line anchors. Consulting with Christian H. and Eric B. suggests the following: Where there are deep drifts, the insulating effect of the snow will create thin areas in the ice cover as it will cease to grow. It will therefore likely be a melt pond in the summer. THe area where there are holes (for instance where the met city hut is) there will be an area of intact ice, however, the hole itself may go through a period of flooding. It is also possible to in areas of deep drifting to get a negative freeboard if there is enough weight to depress the ice. In other words, it is difficult to know the best strategy for snow/ice mitigation now. Met City definitely has an average deep snow depth of about 60 cm from the days of blowing snow. This is compared to a beginning snow depth of 15-20 cm which is still the average depth on most of the MOSAiC flow (according to Martin S.). Matlab browse products indicate all well for tower on 2/18. L2 continues to have excellent data recovery over radio. L1 barely reporting.
2/20/2020 - More blowing and drifting snow. Checked met city. All sensors cleaned "naturally" by high winds and low humidity. Taneil brought the VISSS drive back to the ship for Michael as they should have been done. Taneil was bear guarding on this day at ROV for long line fishing. Matlab browse products indicate all well for tower on 2/19. L2 continues to have excellent data recovery over radio. L1 barely reporting.
2/21/2020 - Michael visited Met City. Still working on VISSS backups. Taneil went on a southern transect chamber measurement event and stopped on the way back to observe a snow pit sampling event. There are (I think) 9 snowpits in snow 1. Most are only a few cm deep and are covered after sampling. It does not look as if they would be an issue for generating artificial turbulence at the met city 11 m tower. The sites have very short marker flats (~30 cm). Matlab browse products indicate all well for tower on 2/20. L2 continues to have excellent data recovery over radio. L1 barely reporting.
2/22/2020 - Taneil and Michael went to L2 via helicopter. Refueled and picked up SD card. D-ship is supposedly closing for about the 3rd time. Worked on backups and data transfers to the MSC. Note: we determined that refueling would be simpler if the the helicopter pilots took the methanol first and dropped off for us and then returned to pick up scientists to return and do the refueling while the helicopter waited. This plan had the added efficiency of not requiring a bear guard. Lights inside the control box may have been left on. Matlab browse products indicate all well for tower on 2/21. L 2 continues to have excellent data recovery over radio. L1 barely reporting.
2/23/2020 - Met City visit. Still watching the ever accumulating drifts. Continuring to work on handover preparation - backups, MCS, cargo, planning. An inordinate amount of time is being spent on developing priority cargo and personnel lists in the event that there is a partial transfer by helicopter. General mood on the ship is very irritated about not so much the uncertainties, but the amount of information being received. Matlab browse products indicate all well for tower on 2/22. L 2 continues to have excellent data recovery over radio. L1 barely reporting.
2/24/2020 - VISSS backup won't fit on disk provided. Switching backup to Lacie. Matlab browse products indicate all well for tower on 2/23. L2 continues to have excellent data recovery over radio. L1 barely reporting. Short disconnect on 23 m mast when data cable was disconnected (again) when clearing snow from cables. Need a better connector wrap than the zip ties. Almost all on ice activities cancelled - OFFICIAL DSHIP END OF LEG II at 0900 UTC. Matlab browse products indicate all well for tower on 2/23. L 2 continues to have excellent data recovery over radio. L1 barely reporting.
2/25/2020 - The wishful thinking twilight has turned into a clear transition away from polar night. It is suddenly getting light quickly. No visit to MET CITY. Expecting the Dranitsyn to make it and do a full changeover. Preparations on-going for handover. Looking good with recent L1 and L2 SD card recoveries and refueling. Expecting to have things in good shape for Leg III (Chris and Jenny). Matlab browse products indicate all well for tower on 2/24. L 2 continues to have excellent data recovery over radio. L1 barely reporting.
2/26/2020 - Met City visit after several days of high winds and blowing snow. Lots of digging to clear drifts against SODAR enclosure in around SODAR antenna inside the enclosure. Very difficult to open and close the enclosure - Could use a retrofit - at least longer bolts. Also cleared all 23 mast (noodle) cables which were buried and hard to free from hard packed snow. The 3 noodle adjustment 'nests' were unburied and are now all sitting in depressions. Michael filming with planatarium camera. Taneil digging. Matlab browse products indicate all well for tower on 2/25. L 2 continues to have excellent data recovery over radio. L1 barely reporting.
2/27/2020 - The curse of the Dranitsyn. Taneil woke to find that both L1 and L2 and abruptly discontinued radio communciations. L2 appeared to go from full operating modelto nothing at 23:00 UTC on 02/26. L1 latest reports were very cold temperatures inside control box (-16 C) with last report at 03:00 2/27. The KD is scheduled to arrive at the MOSAiC floe tomorrow...loss of radio communications seems eerily similar to the loss of iridium communications the day before the Dranitsyn arrived for Leg II. Close communications between PS and KD to make sure that L2 was not disturbed including dropping off an AIS by helicopter. The helicopter pilot also stopped to check ASFS-50 with a go-pro on and confirmed that it was not operating. Error message 40. The radio in the crows nest was also checked. Matlab browse products indicate all well for tower on 2/26.
2/28/2020 - KD arrives. Amazing morning with KD, venus and the moon in a straight line in the morning. Twilight still brightening quickly. Very cold, less tha -35 degees C with forecast to be cold all week and going down to -40 degrees on Friday. Everyone is suddenly interested in the on-board website that we constructed that shows tower temperatures in real time. There is sometimes a marked difference between the 2-meter temperatre and the 40 m (?) temperature where the ship measures. Looks like a rough transfer ahead - the KD is parking a bit over 1 km from the PS. Too cold for helicopter flights. Skidoos not happy. Cranes very not happy. Dranitsyn parks so that gangway cannot be deployed as there is a large ice block in the way. First days are with mummy chair on and off ship for personnel. First ATMOS meeting on the KD. Matlab browse products indicate all well for tower on 2/27.
2/29/2020 - HANDOVER. Met City visit. Flux team, BAS, Winds, UAS. Matlab browse products indicate all well for tower on 2/28
3/1/2020 - HANDOVER Met City visit. Flux teams, BAS Winds, UAS. NOTE: Ship lidar laser still out. Michael working on it with Andie. Matlab browse products indicate all well for tower on 2/29. As it has become lighter and lighter out, we are observing regular daily contrails over the ice camps. It is reported that the night watch has heard United Pilots talking.
3/2/2020 - HANDOVER - Chris and Jenny take over daily reporting. Matlab browse products indicate all well for tower on 3/1
3/3/2020 - TRANSFER SCIENCE CREW BETWEEN PS AND KD.
3/4/2020 - Michael, Eric (logistics), Chris and Leg III logistics) make epic trip to L2 with 2 skidoos and 1 sledge. L2 lives again! Hooray. L2 Efoy and Batteries recoverd. And that is IT for Leg II. -41 to -42 degrees reported at 2 m (Taneil hears this word of mouth). A very large Polyna has opened to the east of the ships. Hopeful that this will be a super highway to start the trip home.