## Sheet1
MOSAiC Flux Systems
Element | Description/Requirements | Deadline | Required Personnel Time | Lead | Support personnel
Instrument Systems
Radiation | Identify radiation suite, determine optimal mitigation strategies, determine power consumption | end Apr 2018 |  | Matt | Ola, Chris, Sara
| Preliminary decisions | end Jan 2018 |  | Matt | Ola, Chris, Sara
| Documentation of power requirements | end Jan 2018 |  | Chris | Sara
Sonic | Identify sonic anemometers, determine optimal mitigation strategies, determine power consumption. Use Metek in Eureka as example for power consumption and rime mitigation tests. | end Jan 2018 |  | Ola | Andre, Matt
Licor | Identify licor that will best handle conditions, mitigation strategy | end Jan 2018 |  | Ola | Andre, Byron, Matt
Met |  | end Jan 2018 |  | Ola | Matt
Snow depth |  | end Jan 2018 |  | Matt | Ola
IR temperature |  | end Jan 2018 |  | Matt | Ola
Camera |  | end Jan 2018 |  | Matt | Ola
Procurement - Prototype |  | end May 2018 |  | Matt | Sara, CIRES
Procurement - Final |  | end Apr 2019
Pre Calibrations | Calibration of all radiation and met sensors | 2019-07-01
Post Calibrations | Calibration of all radiation and met sensors | 2020-12-01
Data and Communications Systems
ASFS data logging | Logging of system data. Central computing (Data logger? MOXA?). Interfacing with power system and communications systems. | 2018-09-01 |  | Sergio | Chris
ASFS communications | Design a low-power system to transfer limited data (~10 kB file / hour) from remote stations to the ship (15-20 km distance); Test | 2018-07-01 |  | Sergio
Tower data logging | Typical tower data logger. Interfacing with wireless communications system back to ship. | 2018-09-01 |  | Sergio | Chris
Tower communications | Design a system to transfer all data in real time from flux tower to ship (~1km range with line-of-sight). Test | 2018-09-01 |  | Sergio
Power Systems
ASFS power system | Design a system to provide required power (50W) for up to 2 months; Integrate and test under realistic conditions. | 2018-09-01 |  | Dave
Tower backup power system | Backup power system in case line power is disconnected. Specify this to last for 3 days, potentially with a limited set of observations/equipment (i.e., possibly not all heaters) | 2018-09-01 |  | Dave
Monitoring
Operational logic | System for optimal operation of systems (heaters, comms, etc.) | 2019-01-01 |  | Dan?
ASFS system monitoring | Interface for monitoring ASFS system health, fuel/battery capacity, location, etc. | 2019-01-01 |  | Dave
Quicklook plotting | Daily plotting system: daily quicklooks with updating in-day plots run hourly, includes data from tower and from remote stations | 2019-07-01 |  | Matt
Structural Design
ASFS full system design | Master design that integrates all ASFS instruments, communications, power supply, on-site computing, and other features. Towable, slingable. Floatation? | 2018-09-01 |  | Dave | Sergio, Matt, Ola
Tower design | Master design for flux tower that integrates all instruments, local data logging, communications, and power. Must include ability to access equipment on daily basis. Must include the ability to "easily" move full tower system. | 2018-09-01 |  | Dave | Sergio, Ola, Matt
Central command | Shipping sea container with some internal modifications for rough office space. (Paul may have a container?) | 2019-02-01 |  | Sergio | Dave, Matt
Data Handling
Data design | File formating, output | 2019-01-01 |  | Sara | Ludovic, Taneil, Matt
On-site data archival system | Data archival and redundant backup system | Spring 2019 |  | Matt
Data transport system | Manual transfer of data to Boulder from the field | Spring 2019 |  | Matt