## Sheet1
MOSAiC Staffing List: Boulder Teams
|  | Atmos Flux (Shupe) |  | Gas Flux (Blomquist) |  | UAS (de Boer) |  | Comms | On Polarstern |  | Full Deployment |  | Ports |  | Vessel |  | Conditions | Comments
Leg | DOE | Sci | Eng | #1 | #2 | Sci | Pilot | Outreach | Start | End | Start | End | Start | End | In | Out
Tromso Port | X | X | X | 5-6 personnel | X | X | X | X |  |  | 2019-09-13 | 2019-09-19 | [5 empty] | Port setup only
Federov | X | Cox | X | X | Hueber (PS) | X | X | Anne Gold | 2019-09-19 | 2019-10-15 | 2019-09-13 | 2019-10-30 | Tromso | Tromso | Federov | Federov | Transition | Site setup only
1 | Shupe | Persson | Costa | Blomquist | Archer | X | X | Amy Richman | 2019-09-19 | 2019-12-15 | 2019-09-13 | 2020-01-04 | Tromso | Tromso | Polarstern | Makarov | Trans/Night
2 | X | Uttal | Gallagher | Howard | Posman | X | X | X | 2019-12-15 | 2020-02-15 | 2019-11-23 | 2020-03-07 | Tromso | Tromso | Makarov | Makarov | Night
3 | X | Cox | Hutchings | Bariteau | Jacobi? | Cassano | Gina Jozef | X | 2020-02-15 | 2020-04-15 | 2020-01-25 | 2020-04-17 | Tromso | Longyearbyen | Makarov | Antonov | Transition
4 | X | Persson | Osborn | Blomquist | Archer | de Boer | Doug Weibel | Michael Kodas? | 2020-04-15 | 2020-06-15 | 2020-04-13 | 2020-06-17 | Longyearbyen | Tromso | Antonov | Oden | Day | 50pax
5 | X | Gallagher | Herrera | Howard | Posman | Radiance Calmer | John Hamilton | Lianna Nixon | 2020-06-15 | 2020-08-15 | 2020-06-01 | 2020-08-30 | Tromso | Tromso | Oden | XueLong | Day | 50pax
6 | X | Shupe | Costa | Blomquist | Angot | X | X | ??? | 2020-08-15 | 2020-10-01 | 2020-08-01 | 2020-10-08 | Tromso | Tromso | XueLong | Polarstern | Day
Options | Shupe | Shupe | Costa | Blomquist | Archer | de Boer | CU Aerospace student
|  | Persson | Ayers | Archer | Posman | Cassano | CU ATOC student
|  | Cox | Osborn | Howard | Angot | CU PostDoc | CU Aerospace Engineer
|  | Hutchings | Pezoa | Bariteau |  |  | Jonathan Hamilton (4 or 5)
|  | Uttal | Christian Herrera
Intrieri
Militzer
Ben Moore
Color Scheme |  | Certain | Discussed
Dean Howard: new postdoc hire with some prior polar field experience
Hans-Werner Jacobi: atmospheric chemist from Univ. Grenoble with a lot of polar experience
Kevin Posman: Steve Archer's tech from Bigelow Lab, w/o much polar experience
Helene Angot: Helmig's postdoc with polar field research experience.