## CruisePlan
MR14-05 Cruise plan, 19:00LST (UCT-11) on 4 Sep. | [17 empty] | Activity
CTD Station No. | add. Information | Lat Deg | Lat Min |  | Lon Deg | Lon Min |  | Lat (N) | Lon (E) | Samp. Dep. (m) | Bot. Dep. (m) | Stn. Time (hr) | Dist. (nm) | Speed (kt) | Transit Time (hr) | Estimated Arraival Time (LT) UTC-11 | Estimated Depature Time (LT) UTC-11 | CTD w/Water sampling | CTD | Turbo MAP | Multiple Core | XCTD | SVP
[16 empty] | Components of Stn. Time (h) |  | 0.3+(K__*2)/1.0/60/60+0.83*(36*20/60/60) | 0.3+(K__*2)/1.0/60/60 | 1 | 0.5 | 0 | 0.25
Dutch Harbor |  | 53 | 54.12 | N | 166 | 31.7 | W | 53.902 | 193.4717 |  |  | 0 | 0 | 0 | 0 | 2013-08-31 07:00 | 2013-08-31 07:00
Cape Mochican |  | 60 | 12 | N | 168 | 0 | W | 60.2 | 192 |  |  | 0 | 380.9196 | 12.3 | 30.9691 | 2013-09-01 13:58 | 2013-09-01 13:58
Cape Romanzof |  | 61 | 47 | N | 167 | 22 | W | 61.7833 | 192.6333 |  |  | 0 | 96.7707 | 12.3 | 7.8675 | 2013-09-01 21:50 | 2013-09-01 21:50
WP5 |  | 62 | 52 | N | 167 | 2 | W | 62.8667 | 192.9667 |  |  | 0 | 65.6604 | 12.3 | 5.3382 | 2013-09-02 03:10 | 2013-09-02 03:10
King Island |  | 64 | 58 | N | 168 | 41 | W | 64.9667 | 191.3167 |  |  | 0 | 133.3068 | 12.3 | 10.8379 | 2013-09-02 14:01 | 2013-09-02 14:01
Prince of Wales |  | 65 | 38.2 | N | 168 | 28 | W | 65.6367 | 191.5333 |  |  | 0 | 40.5653 | 12.3 | 3.298 | 2013-09-02 17:19 | 2013-09-02 17:19
Bering Strait |  | 65 | 38 | N | 168 | 28 | W | 65.6333 | 191.5333 |  |  | 0 | 0.2 | 12.3 | 0.01626 | 2013-09-02 17:20 | 2013-09-02 17:20
1 |  | 65 | 46.33 | N | 168 | 47.64 | W | 65.7722 | 191.206 | 45 | 50 | 0.491 | 11.6059 | 12.3 | 0.94357 | 2013-09-02 18:16 | 2014-09-02 19:15 | 1
2 |  | 67 | 0 | N | 168 | 50 | W | 67 | 191.1667 | 45 | 50 | 0.991 | 73.6761 | 11.1 | 6.6375 | 2014-09-03 01:53 | 2014-09-03 03:12 | 1 |  |  | 1
3 |  | 68 | 0 | N | 168 | 50 | W | 68 | 191.1667 | 45 | 50 | 0.491 | 60 | 11 | 5.4545 | 2014-09-03 08:39 | 2014-09-03 09:12 | 1
WP |  | 68 | 21 | N | 168 | 50 | W | 68.35 | 191.1667 | 45 | 50 | 0 | 21 | 15 | 1.4 | 2014-09-03 10:36 | 2014-09-03 10:36
WP |  | 70 | 39 | N | 162 | 56 | W | 70.65 | 197.0667 | 45 | 50 | 0 | 185.5085 | 15 | 12.3672 | 2014-09-03 22:58 | 2014-09-03 22:58
WP |  | 71 | 19 | N | 157 | 25 | W | 71.3167 | 202.5833 | 45 | 50 | 0 | 115.0326 | 15 | 7.6688 | 2014-09-04 06:38 | 2014-09-04 06:38
WP |  | 71 | 19 | N | 157 | 0 | W | 71.3167 | 203 | 45 | 50 | 0 | 8.0084 | 15 | 0.5339 | 2014-09-04 07:10 | 2014-09-04 07:10
Off Barrow |  | 71 | 18 | N | 156 | 52 | W | 71.3 | 203.1333 | 45 | 50 | 0 | 2.7519 | 15 | 0.18346 | 2014-09-04 07:21 | 2014-09-04 14:20
sta. 004 |  | 73 | 20 | N | 162 | 0 | W | 73.3333 | 198 | 150 | 155 | 1.0493 | 153.7429 | 12 | 12.8119 | 2014-09-05 03:09 | 2014-09-05 04:12 | 1 |  |  | 1
sta. 005 |  | 74 | 0 | N | 164 | 0 | W | 74 | 196 | 295 | 300 | 0.62989 | 52.3341 | 11.5 | 4.5508 | 2014-09-05 08:45 | 2014-09-05 09:23 | 1
XCTD 01 |  |  |  |  | 163 | 48 | W |  | 196.2 | [12 empty] | 1
XCTD 02 |  |  |  |  | 163 | 36 | W |  | 196.4 | [12 empty] | 1
XCTD 03 |  |  |  |  | 163 | 24 | W |  | 196.6 | [12 empty] | 1
XCTD 04 |  |  |  |  | 163 | 12 | W |  | 196.8 | [12 empty] | 1
sta. 006 | SVP, XCTD 05 | 74 | 22.5 | N | 163 | 0 | W | 74.375 | 197 | 455 | 460 | 0.96878 | 27.8128 | 11.5 | 2.4185 | 2014-09-05 11:48 | 2014-09-05 12:46 | 1 |  |  |  | 1 | 1
XCTD 06 |  |  |  |  | 162 | 45 | W |  | 197.25 | [12 empty] | 1
XCTD 07 |  |  |  |  | 162 | 30 | W |  | 197.5 | [12 empty] | 1
XCTD 08 |  |  |  |  | 162 | 15 | W |  | 197.75 | [12 empty] | 1
XCTD 09 | Fixed Point | 74 | 45 | N | 162 | 0 | W | 74.75 | 198 | 1625 | 1630 | 0 | 27.5922 | 11.5 | 2.3993 | 2014-09-05 15:10 | 2014-09-05 15:10 |  |  |  |  | 1
XCTD 10 |  |  |  |  | 161 | 40 | W |  | 198.3333 | [12 empty] | 1
XCTD 11 |  |  |  |  | 161 | 20 | W |  | 198.6667 | [12 empty] | 1
7 |  | 75 | 7.5 | N | 161 | 0 | W | 75.125 | 199 | 2265 | 2270 | 1.7243 | 27.3747 | 11.5 | 2.3804 | 2014-09-05 17:33 | 2014-09-05 19:16 | 1
XCTD 12 |  | 74 | 52.5 | N |  |  |  | 74.875 | [13 empty] | 1
XCTD 13 |  | 74 | 37.5 | N |  |  |  | 74.625 | [13 empty] | 1
sta. 008 |  | 74 | 22.5 | N | 161 | 0 | W | 74.375 | 199 | 1105 | 1110 | 1.0799 | 45 | 11.5 | 3.913 | 2014-09-05 23:11 | 2014-09-06 00:16 | 1
XCTD 14 |  |  |  |  | 161 | 20 | W |  | 198.6667 | [12 empty] | 1
XCTD 15 |  |  |  |  | 161 | 40 | W |  | 198.3333 | [12 empty] | 1
9 | Fixed Point | 74 | 45 | N | 162 | 0 | W | 74.75 | 198 | 1625 | 1630 | 3.3688 | 27.5922 | 11.5 | 2.3993 | 2014-09-06 02:40 | 2014-09-06 06:02 | 1 |  | 1 | 1 |  | 2
32 |  | 72 | 12 | N | 156 | 0 | W | 72.2 | 204 | 283 | 288 | #REF! | 10796.9576 | 8 | 1349.6197 | 1900-02-24 05:37 | #REF! | 1
33 |  | 72 | 24 | N | 157 | 0 | W | 72.4 | 203 | 301 | 306 | #REF! | 21.8351 | 11 | 1.985 | #REF! | #REF! |  | 1
34 |  | 72 | 36 | N | 158 | 0 | W | 72.6 | 202 | 192 | 197 | #REF! | 21.6686 | 11 | 1.9699 | #REF! | #REF! | 1
35 |  | 72 | 48 | N | 159 | 0 | W | 72.8 | 201 | 191 | 196 | #REF! | 21.5024 | 11 | 1.9548 | #REF! | #REF! |  | 1
36 |  | 73 | 0 | N | 160 | 0 | W | 73 | 200 | 189 | 194 | #REF! | 21.3367 | 11 | 1.9397 | #REF! | #REF! | 1
37 |  | 73 | 12 | N | 161 | 0 | W | 73.2 | 199 | 332 | 337 | #REF! | 21.1714 | 11 | 1.9247 | #REF! | #REF! |  | 1
38 |  | 73 | 24 | N | 162 | 0 | W | 73.4 | 198 | 181 | 186 | #REF! | 21.0065 | 11 | 1.9097 | #REF! | #REF! | 1 |  | 1
39 |  | 73 | 36 | N | 163 | 0 | W | 73.6 | 197 | 137 | 142 | #REF! | 20.8421 | 11 | 1.8947 | #REF! | #REF! |  | 1
40 |  | 73 | 48 | N | 164 | 0 | W | 73.8 | 196 | 195 | 200 | #REF! | 20.6781 | 11 | 1.8798 | #REF! | #REF! | 1
41 |  | 74 | 0 | N | 165 | 0 | W | 74 | 195 | 192 | 197 | #REF! | 20.5147 | 11 | 1.865 | #REF! | #REF! |  | 1
42 |  | 74 | 12 | N | 166 | 0 | W | 74.2 | 194 | 252 | 257 | #REF! | 20.3517 | 11 | 1.8502 | #REF! | #REF! | 1
43 |  | 74 | 24 | N | 167 | 0 | W | 74.4 | 193 | 306 | 311 | #REF! | 20.1893 | 11 | 1.8354 | #REF! | #REF! |  | 1
44 |  | 74 | 36 | N | 168 | 0 | W | 74.6 | 192 | 251 | 256 | #REF! | 20.0275 | 11 | 1.8207 | #REF! | #REF! | 1 |  |  | 1
45 |  | 74 | 48 | N | 169 | 0 | W | 74.8 | 191 | 201 | 206 | #REF! | 19.8662 | 11 | 1.806 | #REF! | #REF! |  | 1
| XCTD | 76 | 46.8 | N | 171 | 42 | W | 76.78 | 188.3 | 2164 | 2169 | #REF! | 125.2792 | 12 | 10.4399 | #REF! | #REF! | [5 empty] | 8
46 | Planned FX Sta | 77 | 0 | N | 172 | 0 | W | 77 | 188 | 500 | 2151 | #REF! | 13.817 | 12 | 1.1514 | #REF! | #REF! | 1
| XCTD-53 | 77 | 0 | N | 172 | 30 | W | 77 | 187.5 |  |  | #REF! | 6.7485 | 12 | 0.56238 | #REF! | #REF! | [5 empty] | 1
53 |  | 77 | 0 | N | 173 | 0 | W | 77 | 187 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-54 | 77 | 0 | N | 173 | 30 | W | 77 | 186.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
54 |  | 77 | 0 | N | 174 | 0 | W | 77 | 186 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-55 | 76 | 55 | N | 173 | 40 | W | 76.9167 | 186.3333 |  |  | #REF! | 6.7356 | 11 | 0.61233 | #REF! | #REF! | [5 empty] | 1
| XCTD-56 | 76 | 50 | N | 173 | 20 | W | 76.8333 | 186.6667 |  |  | #REF! | 6.7547 | 11 | 0.61406 | #REF! | #REF! | [5 empty] | 1
| XCTD-57 | 76 | 45 | N | 173 | 0 | W | 76.75 | 187 |  |  | #REF! | 6.7737 | 11 | 0.61579 | #REF! | #REF! | [5 empty] | 1
| XCTD-58 | 76 | 40 | N | 172 | 40 | W | 76.6667 | 187.3333 |  |  | #REF! | 6.7929 | 11 | 0.61753 | #REF! | #REF! | [5 empty] | 1
| XCTD-59 | 76 | 35 | N | 172 | 20 | W | 76.5833 | 187.6667 |  |  | #REF! | 6.8121 | 11 | 0.61928 | #REF! | #REF! | [5 empty] | 1
55 |  | 76 | 30 | N | 172 | 0 | W | 76.5 | 188 | 500 |  | #REF! | 6.8313 | 11 | 0.62103 | #REF! | #REF! | 1
| XCTD-60 | 76 | 37.5 | N | 172 | 0 | W | 76.625 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
56 |  | 76 | 45 | N | 172 | 0 | W | 76.75 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-61 | 76 | 52.5 | N | 172 | 0 | W | 76.875 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
| XCTD-62 | 77 | 0 | N | 172 | 0 | W | 77 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
| XCTD-63 | 77 | 7.5 | N | 172 | 0 | W | 77.125 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
57 |  | 77 | 15 | N | 172 | 0 | W | 77.25 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-64 | 77 | 22.5 | N | 172 | 0 | W | 77.375 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
58 |  | 77 | 30 | N | 172 | 0 | W | 77.5 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-65 | 77 | 25 | N | 171 | 40 | W | 77.4167 | 188.3333 |  |  | #REF! | 6.6228 | 11 | 0.60207 | #REF! | #REF! | [5 empty] | 1
| XCTD-66 | 77 | 20 | N | 171 | 20 | W | 77.3333 | 188.6667 |  |  | #REF! | 6.6415 | 11 | 0.60377 | #REF! | #REF! | [5 empty] | 1
| XCTD-67 | 77 | 15 | N | 171 | 0 | W | 77.25 | 189 |  |  | #REF! | 6.6602 | 11 | 0.60547 | #REF! | #REF! | [5 empty] | 1
| XCTD-68 | 77 | 10 | N | 170 | 40 | W | 77.1667 | 189.3333 |  |  | #REF! | 6.6789 | 11 | 0.60718 | #REF! | #REF! | [5 empty] | 1
| XCTD-69 | 77 | 5 | N | 170 | 20 | W | 77.0833 | 189.6667 |  |  | #REF! | 6.6978 | 11 | 0.60889 | #REF! | #REF! | [5 empty] | 1
59 |  | 77 | 0 | N | 170 | 0 | W | 77 | 190 | 500 |  | #REF! | 6.7167 | 11 | 0.61061 | #REF! | #REF! | 1
| XCTD-70 | 77 | 0 | N | 170 | 30 | W | 77 | 189.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
60 |  | 77 | 0 | N | 171 | 0 | W | 77 | 189 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-71 | 77 | 0 | N | 171 | 30 | W | 77 | 188.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
61 | FX Sta | 77 | 0 | N | 172 | 0 | W | 77 | 188 | 2146 | 2151 | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 2 |  |  |  | 1
61 | FX Sta | 77 | 0 | N | 172 | 0 | W | 77 | 188 | 2146 | 2151 | 0 | 0 | 0 | 0 | 2013-09-25 | 2013-09-25
| XCTD-53 | 77 | 0 | N | 172 | 30 | W | 77 | 187.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | 2013-09-25 00:37 | #REF! | [5 empty] | 1
53 |  | 77 | 0 | N | 173 | 0 | W | 77 | 187 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-54 | 77 | 0 | N | 173 | 30 | W | 77 | 186.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
54 |  | 77 | 0 | N | 174 | 0 | W | 77 | 186 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-55 | 76 | 55 | N | 173 | 40 | W | 76.9167 | 186.3333 |  |  | #REF! | 6.7356 | 11 | 0.61233 | #REF! | #REF! | [5 empty] | 1
| XCTD-56 | 76 | 50 | N | 173 | 20 | W | 76.8333 | 186.6667 |  |  | #REF! | 6.7547 | 11 | 0.61406 | #REF! | #REF! | [5 empty] | 1
| XCTD-57 | 76 | 45 | N | 173 | 0 | W | 76.75 | 187 |  |  | #REF! | 6.7737 | 11 | 0.61579 | #REF! | #REF! | [5 empty] | 1
| XCTD-58 | 76 | 40 | N | 172 | 40 | W | 76.6667 | 187.3333 |  |  | #REF! | 6.7929 | 11 | 0.61753 | #REF! | #REF! | [5 empty] | 1
| XCTD-59 | 76 | 35 | N | 172 | 20 | W | 76.5833 | 187.6667 |  |  | #REF! | 6.8121 | 11 | 0.61928 | #REF! | #REF! | [5 empty] | 1
55 |  | 76 | 30 | N | 172 | 0 | W | 76.5 | 188 | 500 |  | #REF! | 6.8313 | 11 | 0.62103 | #REF! | #REF! | 1
| XCTD-60 | 76 | 37.5 | N | 172 | 0 | W | 76.625 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
56 |  | 76 | 45 | N | 172 | 0 | W | 76.75 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-61 | 76 | 52.5 | N | 172 | 0 | W | 76.875 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
| XCTD-62 | 77 | 0 | N | 172 | 0 | W | 77 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
| XCTD-63 | 77 | 7.5 | N | 172 | 0 | W | 77.125 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
57 |  | 77 | 15 | N | 172 | 0 | W | 77.25 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-64 | 77 | 22.5 | N | 172 | 0 | W | 77.375 | 188 |  |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | [5 empty] | 1
58 |  | 77 | 30 | N | 172 | 0 | W | 77.5 | 188 | 500 |  | #REF! | 7.5 | 11 | 0.68182 | #REF! | #REF! | 1
| XCTD-65 | 77 | 25 | N | 171 | 40 | W | 77.4167 | 188.3333 |  |  | #REF! | 6.6228 | 11 | 0.60207 | #REF! | #REF! | [5 empty] | 1
| XCTD-66 | 77 | 20 | N | 171 | 20 | W | 77.3333 | 188.6667 |  |  | #REF! | 6.6415 | 11 | 0.60377 | #REF! | #REF! | [5 empty] | 1
| XCTD-67 | 77 | 15 | N | 171 | 0 | W | 77.25 | 189 |  |  | #REF! | 6.6602 | 11 | 0.60547 | #REF! | #REF! | [5 empty] | 1
| XCTD-68 | 77 | 10 | N | 170 | 40 | W | 77.1667 | 189.3333 |  |  | #REF! | 6.6789 | 11 | 0.60718 | #REF! | #REF! | [5 empty] | 1
| XCTD-69 | 77 | 5 | N | 170 | 20 | W | 77.0833 | 189.6667 |  |  | #REF! | 6.6978 | 11 | 0.60889 | #REF! | #REF! | [5 empty] | 1
59 |  | 77 | 0 | N | 170 | 0 | W | 77 | 190 | 500 |  | #REF! | 6.7167 | 11 | 0.61061 | #REF! | #REF! | 1
| XCTD-70 | 77 | 0 | N | 170 | 30 | W | 77 | 189.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
60 |  | 77 | 0 | N | 171 | 0 | W | 77 | 189 | 500 |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 1
| XCTD-71 | 77 | 0 | N | 171 | 30 | W | 77 | 188.5 |  |  | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | [5 empty] | 1
61 | FX Sta | 77 | 0 | N | 172 | 0 | W | 77 | 188 | 2146 | 2151 | #REF! | 6.7485 | 11 | 0.6135 | #REF! | #REF! | 2 |  |  |  | 1
61 | FX Sta | 77 | 0 | N | 172 | 0 | W | 77 | 188 | 2146 | 2151 | 0 | 0 | 0 | 0 | 2013-09-25 | 2013-09-25
62 |  | 76 | 40 | N | 172 | 0 | W | 76.6667 | 188 | 2164 | 2169 | #REF! | 20 | 11 | 1.8182 | 2013-09-25 01:49 | #REF! | 1
63 |  | 76 | 15 | N | 174 | 0 | W | 76.25 | 186 | 2195 | 2200 | #REF! | 37.61 | 11 | 3.4191 | #REF! | #REF! | 1 |  | 1
64 |  | 76 | 0 | N | 175 | 30 | W | 76 | 184.5 | 2006 | 2011 | #REF! | 26.2831 | 11 | 2.3894 | #REF! | #REF! | 1 |  | 1
65 |  | 75 | 45 | N | 176 | 30 | W | 75.75 | 183.5 | 1699 | 1704 | #REF! | 20.9618 | 11 | 1.9056 | #REF! | #REF! | 1
66 |  | 75 | 36 | N | 177 | 10 | W | 75.6 | 182.8333 | 1228 | 1233 | #REF! | 13.3771 | 11 | 1.2161 | #REF! | #REF! | 1
67 |  | 75 | 30 | N | 177 | 55 | W | 75.5 | 182.0833 | 998 | 1003 | #REF! | 12.7315 | 11 | 1.1574 | #REF! | #REF! | 1
68 |  | 75 | 20 | N | 178 | 30 | W | 75.3333 | 181.5 | 832 | 837 | #REF! | 13.329 | 11 | 1.2117 | #REF! | #REF! | 1
69 |  | 75 | 6 | N | 179 | 0 | W | 75.1 | 181 | 398 | 403 | #REF! | 15.9561 | 11 | 1.4506 | #REF! | #REF! | 1
70 |  | 75 | 0 | N | 180 | 0 | W | 75 | 180 | 245 | 250 | #REF! | 16.6008 | 11 | 1.5092 | #REF! | #REF! | 1
71 |  | 75 | 0 | N | 179 | 0 | W | 75 | 181 | 220 | 225 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1 |  | 1
72 |  | 75 | 0 | N | 178 | 0 | W | 75 | 182 | 302 | 307 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1 |  | 1
73 |  | 75 | 0 | N | 177 | 0 | W | 75 | 183 | 275 | 280 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
74 |  | 75 | 0 | N | 176 | 0 | W | 75 | 184 | 239 | 244 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
75 |  | 75 | 0 | N | 175 | 0 | W | 75 | 185 | 257 | 262 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
76 |  | 75 | 0 | N | 174 | 0 | W | 75 | 186 | 281 | 286 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
77 |  | 75 | 0 | N | 173 | 0 | W | 75 | 187 | 331 | 336 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
78 | CAP | 75 | 12.42 | N | 172 | 32.67 | W | 75.207 | 187.4555 | 442 | 447 | 10 | 14.2695 | 2.5 | 5.7078 | #REF! | #REF! | 1 |  | 1 | 1 | 1
| WP | 76 | 30 | N | 172 | 32.67 | W | 76.5 | 187.4555 |  |  | #REF! | 77.58 | 12 | 6.465 | #REF! | #REF!
| XCTD | 75 | 0 | N | 172 | 32.67 | W | 75 | 187.4555 | 348 | 353 | #REF! | 90 | 12 | 7.5 | #REF! | #REF! | [5 empty] | 6
79 |  | 75 | 0 | N | 172 | 0 | W | 75 | 188 | 354 | 359 | #REF! | 8.4556 | 11 | 0.76869 | #REF! | #REF! | 1 |  | 1
80 |  | 75 | 0 | N | 171 | 0 | W | 75 | 189 | 352 | 357 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1 |  | 1
81 |  | 75 | 0 | N | 170 | 0 | W | 75 | 190 | 275 | 280 | #REF! | 15.5291 | 11 | 1.4117 | #REF! | #REF! | 1
82 |  | 75 | 0 | N | 168 | 0 | W | 75 | 192 | 173 | 178 | #REF! | 31.0583 | 11 | 2.8235 | #REF! | #REF! | 1
83 |  | 75 | 0 | N | 166 | 0 | W | 75 | 194 | 461 | 466 | #REF! | 31.0583 | 11 | 2.8235 | #REF! | #REF! | 1
84 |  | 75 | 0 | N | 164 | 0 | W | 75 | 196 | 660 | 665 | #REF! | 31.0583 | 11 | 2.8235 | #REF! | #REF! | 1
85 | NAP | 75 | 0.06 | N | 162 | 0.91 | W | 75.001 | 197.9848 | 1970 | 1975 | 12 | 30.8218 | 11 | 2.802 | #REF! | #REF! | 1 |  | 1 | 1 | 1
| WP | 76 | 0 | N | 162 | 0 | W | 76 | 198 |  |  | #REF! | 59.9404 | 12 | 4.995 | #REF! | #REF!
| XCTD | 75 | 0 |  | 162 | 0 | W | 75 | 198 | 1887 | 1892 | #REF! | 60 | 12 | 5 | #REF! | #REF! | [5 empty] | 4
86 |  | 74 | 30 | N | 162 | 0 | W | 74.5 | 198 | 1610 | 1615 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1 |  | 1 | 1
87 |  | 74 | 0 | N | 162 | 0 | W | 74 | 198 | 366 | 371 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1 |  | 1
88 |  | 73 | 30 | N | 162 | 0 | W | 73.5 | 198 | 182 | 187 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1
89 |  | 73 | 0 | N | 162 | 0 | W | 73 | 198 | 80 | 85 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1
90 |  | 72 | 30 | N | 162 | 0 | W | 72.5 | 198 | 47 | 52 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1
91 |  | 69 | 0 | N | 168 | 45 | W | 69 | 191.25 | 45 | 50 | #REF! | 248.8551 | 11 | 22.6232 | #REF! | #REF! | 1
92 |  | 68 | 30 | N | 168 | 45 | W | 68.5 | 191.25 | 46 | 51 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1
93 |  | 68 | 0 | N | 168 | 45 | W | 68 | 191.25 | 45 | 50 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1
94 |  | 67 | 30 | N | 168 | 45 | W | 67.5 | 191.25 | 46 | 51 | #REF! | 30 | 11 | 2.7273 | #REF! | #REF! | 1 |  | 1
95 | CS11 | 67 | 45 | N | 168 | 30 | W | 67.75 | 191.5 | 42 | 47 | #REF! | 16.0501 | 11 | 1.4591 | #REF! | #REF! | 1 |  | 1
96 | CS12 | 67 | 52.5 | N | 168 | 15 | W | 67.875 | 191.75 | 52 | 57 | #REF! | 9.3988 | 11 | 0.85444 | #REF! | #REF! | 1
97 | CS13 | 68 | 0 | N | 168 | 0 | W | 68 | 192 | 53 | 58 | #REF! | 9.3806 | 11 | 0.85278 | #REF! | #REF! | 1
98 | CS14 | 68 | 6 | N | 167 | 40 | W | 68.1 | 192.3333 | 49 | 54 | #REF! | 9.5859 | 11 | 0.87145 | #REF! | #REF! | 1
99 | CS15 | 68 | 12 | N | 167 | 20 | W | 68.2 | 192.6667 | 41 | 46 | #REF! | 9.5607 | 11 | 0.86915 | #REF! | #REF! | 1
100 | CS16 | 68 | 15 | N | 167 | 12.15 | W | 68.25 | 192.7975 | 38 | 43 | #REF! | 4.1809 | 11 | 0.38008 | #REF! | #REF! | 1
101 | CS17 | 68 | 18 | N | 167 | 3 | W | 68.3 | 192.95 | 32 | 37 | #REF! | 4.5245 | 11 | 0.41132 | #REF! | #REF! | 1
102 |  | 67 | 0 | N | 168 | 45 | W | 67 | 191.25 | 39 | 44 | #REF! | 87.1115 | 11 | 7.9192 | #REF! | #REF! | 1
Bering Strait |  | 65 | 38 | N | 168 | 28 | W | 65.6333 | 191.5333 |  |  | #REF! | 82.2838 | 11 | 7.4803 | #REF! | #REF!
Dutch Harbor |  | 53 | 54.12 | N | 166 | 31.7 | W | 53.902 | 193.4717 |  |  | #REF! | 706.3116 | 11 | 64.2101 | #REF! | #REF!
[15 empty] | JST | #REF!
[12 empty] | #REF! | 13907.275 |  |  |  |  | 78 | 7 | 14 | 7 | 19 | 59
25937.0678
Formulas:
Estimated Depature Time (LT) UTC-11 = [Estimated Arraival Time (LT) UTC-11]+[Stn. Time (hr)]/24
Estimated Arraival Time (LT) UTC-11 = [Estimated Depature Time (LT) UTC-11, row above]+[Transit Time (hr)]/24
Estimated Arraival Time (LT) UTC-11 = R20+[Transit Time (hr)]/24